**Supervisory Meeting**

**Ref:** SM-01

**Student:** Maxwell Knox (1507205)

**Supervisor:** Robert Lothian

**Date:** 07/10/16

**Discussion:**

* Initial ideas for the project were discussed - it had been decided that the project would focus on WebVR and e-learning, however, the specifics had not yet been confirmed.
* Discussed possibilities for the subject of the application, such as a VR yoga trainer, or a VR solar system.
* Rob advised to consider the scope of the project and to make sure it was achievable.

**Tasks for following meeting:**

* Decide upon a focus for the webVR application
* Begin to plan out the project proposal and prepare a draft copy.
* Continue to investigate potential source material for literature review.

**Supervisory Meeting**

**Ref:** SM-02

**Student:** Maxwell Knox (1507205)

**Supervisor:** Robert Lothian

**Date:** 21/10/16

**Minutes:**

* Finalisation of the project specifications were discussed. I had decided that rather than developing a complete WebVR based e-learning application, I would instead use the project to investigate the suitability of WebVR as a medium for e-learning.
* Discussed the idea that the project would be broadly be composed of two major phases. An initial research phase where I investigate and discuss the potential for WebVR as a tool for learning, through both an in-depth literature review and a critical analysis of existing applications of WebVR. The second phase would involve developing a range of WebVR testing environments where I implement the techniques and best practices that had been learned in the research phase.
* We discussed the requirements for the first submission - the project proposal. We talked about elements of the proposal such as the initial, mini literature review and the timetable for project deliverables and milestones.
* We discussed the draft proposal and how it could be improved prior to submission.

**Tasks for following meeting:**

* Prepare and submit project proposal.
* Discuss the final submission and grade of the project proposal.
* Continue to investigate potential source material for the literature review.
* Test early stages of development

**Supervisory Meeting**

**Ref:** SM-03

**Student:** Maxwell Knox (1507205)

**Supervisor:** Robert Lothian

**Date:** 04/11/16

**Minutes:**

**Discussed the final proposal**

**Tasks for following meeting:**

**Supervisory Meeting**

**Ref:** SM-04

**Student:** Maxwell Knox (1507205)

**Supervisor:** Robert Lothian

**Date:**

**Minutes:**

**Tasks for following meeting:**